## Project Timeline
Project Timeline
Project Milestones
Date | Milestone | Assigned To | Position | Baseline | Project Timeline Tip
2016-09-05 | Project Start | All Team | 20 | 0 | Use the Position field in the Project Milestones table to place the milestone labels where you want! Use positive numbers to position them above the timeline and negative numbers to position them below.
2016-09-19 | Cari Ide dan buat slide | Andik Sugianto | 10 | 0
2016-09-19 | Buat Timeline | Andik Sugianto | -10 | 0
2016-10-03 | Buat Flowchart | Muhammad Shafwan Al Farisy | 25 | 0
2016-10-17 | Buat Rancangan Interface | Azhar Krisna Pratama | 15 | 0
2016-10-17 | Develope System | All Team | -15 | 0
2016-11-07 | Pengujian Sistem | All Team | 15 | 0
2016-11-14 | Implementasi Sistem | All Team | -20 | 0
2016-12-19 | Project End |  | 5 | 0